## Development
Project Name
Frontend URL
Backend URL
Username
Password
Category | Checklist Item | Developer Status | QA Status
Development Checklist
Store Configuration | Update Store URL Ensure old URLs no longer redirect to staging/demo environments.
Disable Password Protection Disable storefront password for public access.
Favicon Remove Shopify/Magento or old site favicon. Path: Sales channels → Online Store → [Current Live theme] → Theme → Customize → Theme Settings → Logo → Favicon image
Content & Design Cleanup | Remove Dummy Content Delete test data, products, customers, backup themes, obsolete files, testing emails.
Remove Theme References Clear all mentions of development or unused themes.
Newsletter Subscription Match functionality to SRS & design mockups.
Confirm Product Inventory Setup Before going live, confirm with the client which inventory configuration they would like to use. You may need to perform an additional product import with updated stock levels prior to the launch.
Shipping Origin & Method Set and verify shipping profiles, weights, and dimensions.
Tax Settings: Settings → Taxes and duties → Regional settings → click the region — Correct navigation. Base taxes section, specify the tax rates manually or Reset to default
Contact Information: Ensure all the store information and email addresses are set. You will be able to find these in Settings → General → Store details Settings → Notifications → Sender email Settings → Notifications → Staff notifications
Payment Gateways: Settings → Payments Shopify Payments PayPal (check cancel & payment redirect to live) Credit Cards (real transaction test recommended)
Purchase App Licenses: Ensure correct plan and purchase of paid apps.
Remove Unused Apps
Packing Slip Design Upload logo and insert in packing slip Liquid template. Path: Settings → Shipping and delivery → Packing slips → Edit.
Signature Validation If the project includes an SEO package, signature verification is not required. If the project does not include an SEO package, verify the signature on the home page only.
ABN Field Format: Must support 11-digit numeric entry, allow spaces.
Algolia App Indexing: Apps → Algolia AI Search & Discovery → Configuration → Indexing Ensure the Product Variants and Collections indexes are up to date. If you've made any changes to products or collections, click "Re-index" to update the data in Algolia.
Verify that users can create an account during checkout if required and confirm welcome email is sent post-registration correctly.
Test all social media icons to ensure they link to the correct profiles.
Ensure the privacy policy is accessible, up-to-date, and visible on key pages, including the checkout page.
Ensure server-side validation is in place for Google reCAPTCHA (disable JS and test forms)
Cross-Browser/Device Testing | Customize Email Templates
Test on iPhone (including Safari and Chrome)
Test on Android (including default browser)
Test in all major browsers (Chrome, Firefox, Safari, Edge)
Ensure no console errors in Developer Tools (especially Firefox)
Email & Notifications | Remove any test email IDs
Verify all forms send emails correctly
Confirm contact form stores submissions in the database (plugin installed)
Add phone and email info to email templates header
Email Templates: Make sure you uploaded logo. Settings → Notifications → Customer notifications → Customize email template
Test email deliverability via www.email-tester.com – Score should be 7/10 or higher

## SEO
Category | Checklist Item | Developer Status | QA Status
SEO Checklist
On-Page SEO | For all Pages, Check in Page Source below things must be followed: <meta name="robots" content="INDEX, FOLLOW" /> <link rel="canonical" href="http://www.(Page URL)" />
Noindex, nofollow Meta Tags: /account/register /account/login /cart /checkout /404 /wishlist pages
Set meta title and descriptions for all pages
Noindex,follow meta tags on Catalogue Search
Enable Canonical URLs & Fix Trailing Slash Issue Google treats the following two URLs as separate pages, which can lead to duplicate content and SEO issues: https://www.example.com.au/sale-items/ https://www.example.com.au/sale-items Enable canonical URLs for categories and products. Fix trailing slash issues via canonical/301 redirects. Custom Canonical for CMS, categories, subcategories.
Sorting, Filters & Search URLs: Apply noindex, follow to query/filtered URLs. Example https://justwashroom.com.au/collections/all?sort_by=best-selling https://justwashroom.com.au/collections/all?filter.v.price.gte=203&filter.v.price.lte=1298&sort_by=price-ascending https://justwashroom.com.au/collections/all?sort_by=price-ascending Sort by ascending and descending
For Pagination - Set canonical for main page
Add ALT and TITLE attributes for all images in the code.
Set proper H1 tags (only one per page, page title in H1)
Set H2 and H3 tags as well
Keep all HEADING tags only body part
Set Image name(URL) as per relevant section
Require FAQs section on home page
Technical SEO | WWW redirection configured
Sitemap
Update Robots.txt
Implement 301 redirects if URLs changed from old site
Blog Section
Configure Google components/APIs from google.com.au (preferably, or google.com)
Require to change URL structure if get notification from onshore
Hide directory browsing for /uploads folder
Analytics & Tracking | Google Analytics
For Ecomm - Enhance e-comm tracking (Events of Purchase, add to cart, view item, view item list, view cart, begin checkout)
Performance & Security | Achieve A+ Security Header Score
Verify site with Google’s Mobile-Friendly Test
Gtmetrix
Google Pagespeed (Desktop + Mobile)
Minify & Merge JS/CSS/HTML
Verify SSL Certificate
Set cache expiration headers for HTML, JS, CSS, and images
The content section on the homepage should be displayed without a scrollbar - depend on the content legnth
Resize banner and other large images appropriately
Check for broken links (404s)
Structured Data / Schema | For Service Based - Do a schema code for breadcrumb, faqs, blog
For Ecomm - Do a schema code for breadcrumb, Product, blog, faqs
Suggested Extra Elements: | Requires Google Reviews section on home page - if applicable